## Day-wise
Day-wise Plan
Day | Module | Description
1 | Project Understanding | - Understanding Project scope and requirements - Create Team/Groups - Project Allotment - Understanding Project Entities - Defining roles/responsibilities among team members - Creating DB Diagrams - Project wiring
2 | Backend Implementation | - Database Design - Creating Entities in Database - Creating and Running Queries
3 | Backend Implementation | - Creating entites in backend logic - Conneting Database entities with business logic - Testing business logic
4 | Backend Implementation | - Business logic implementation - REST API Creation - Unit Testing
5 | Backend Implementation | - REST API Creation - Automation Testing
6 | UI Implementation | - UI Project setup - Choosing App theme - Choosing Web ingredients - Layout discussion - Figma Design Tool - App Wiring
7 | UI Implementation | - Creating Components with Dummy Data - Combining components - Component Hierarchy
8 | UI Implementation | - UI Design - UI Layout - UI Logic Implementation
9 | Runnable App | - Connecting BE with FE
10 | Runnable App | - Connecting BE with FE - CI/CD & App Deployment
11 | Project Demonstration | - Project Review & Evaluation

## Deliverables
Sprint | No.Of Days | Sprint Details | Sprint Deliverable
1 | 1 | Project Setup and Configuration - Running skeletal project , creating the database design and models | Database Design and Models
2 | 2 | Business logic implementation - Understanding project requirments and implement business logic with unit test project | Business Logic & Unit Testing
3 | 2 | API Implementation - develop the REST API of the project | Rest API, Test the API using Postman/Swagger
4 | 3 | UI Implementation - develop the frontend/user interface of the project | User Interface of the Application
5 | 2 | Additional features Implementation and Project Review | Integrate the frontend and backend. Runnable application

## Assessments
S. No. | Assessment | Question distribution | Date | Duration | # Questions | Pattern | Mode
1 | Pre-Screening Test | Java, SpringBoot, Angular/React | Day 01 - Session 01 | 90 Minutes | 50 | Objective Type | Online
2 | API Development Coding Challenge | Java, SpringBoot | Day 05 - Session 04 | 60 Minutes | 2 | Coding | Classroom
3 | UI Coding Challenge | Frontend / UI (Angular/React) | Day 09 - Session 04 | 60 Minutes | 2 | Coding | Classroom
4 | Post-assessment Test | Java, SpringBoot, Git, Cloud, Docker, Kubernetes, Angular/React | Day 10 - Session 04 | 90 Minutes | 50 | Objective Type | Online
5 | Project Presentation | Runnable project demonstration | Day 11 | Full Day | 0 | Presentation | Classroom