## Sheet1
Revised Day-wise Plan
Day | Module | Description
1 | Project Understanding | - Understanding Project scope and requirements - Create Team/Groups - Project Allotment - Understanding Project Entities - Defining roles/responsibilities among team members - Creating DB Diagrams - Project wiring
2 | Backend Implementation | - Spring Intro - SpringBoot Intro - SpringBoot Demo - CRUD operation demo - Identifying entities by candidates as per project assigned
3 | Backend Implementation | - Creating entites in backend logic - Conneting Database entities with business logic - Understanding Microservice feature
4 | Backend Implementation | - Understanding Docker basics to build images - Understanding Spring Config Server for external configuration - Environment Variables / JVM Variables - Spring Profiles - Project Business logic implementation - Project REST API Creation - Started Unit Testing - Performed CRUD Operation using SpringBoot for project by participants
5 | Backend Implementation | - Understanding Edge Server - Understanding gateway server - Implementing edge and gateway server in project - Implementing communication between microservices using OpenFeign
6 | Backend Implementation | - Spring Security, Routing, Service Discovery / Registration, Inter-service communication - Understanding Observability and messaging service - Writing Tests
7 | Backend Implementation | - Implementing Messaging Service and Obserability in Project - Building the docker images for project - K8s and various commands - Integrating additional features from GCP in project
8 | UI Implementation (Angular) | - Creating Components with Dummy Data - Combining components - Component Hierarchy - Writing frontend tests for components
9 | UI Implementation (Angular) | - UI Design - UI Layout - UI Logic Implementation - Writing tests using Jasmine and Karma
10 | Runnable App | - Connecting BE with FE - App Deployment on GCP
11 | Project Demonstration | - Project Review & Evaluation